## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more team members join after the initial formation of the team | 5 | 2 | 2 | 1*4*2=8 | team leader and all members | 2025-05-20 | Get new team members up to date on the current progress/plan and reassign team lead roles. | Two team members joined a week into the class, so we reassigned our team lead roles and quickly got them up to speed on our plans for the project. | Open
| Lack of motivation or responsibility | One or more team members aren't fairly contributing to the project | 2 | 5 | 5 | 4*1*5=20 | team leader and all members | 2025-06-01 | Start with a private discussion between the team leader and team member about their responsibilities and why they may not be contributing. If this does not resolve the problem, then work with team members to redistribute the work that isn't being completed. | No one has shown a lack of motivation so far | Open
Communication | duplicate work | Multiple team members are working on the same task individually | 2 | 3 | 2 | 4*3*2=24 | team leader and requirement leader | 2025-05-20 | Have weekly meetings to discuss who is responsible for each task and maintain communication in Discord throughout the week. | Not an issue so far | Open
| Team member avilability conflicts | Team members have different schedules, making it difficult to meet outisde of regular meetings to discuss quick issues or updates | 4 | 3 | 2 | 2*3*2=12 | Team leader | 2025-05-16 | Set up shared doc. Encourage members to post updates or questions in group chat/shared doc when real-time meetings aren't possible | Started using shared doc to keep up with iteration requirements | Open
| useless work | One or more team members work on something that isn't necessary or incorrectly complete a task | 2 | 3 | 3 | 4*3*3=36 | all team members | 2025-05-20 | Have weekly meetings to discuss responsibilities and have team members review each other's work | Not an issue so far | Open
| inconsistent work | One or more team members aren't on the same page in terms of what needs to be done and how to do it | 2 | 3 | 2 | 4*3*2=24 | team leader and requirement leader | 2025-05-20 | Have weekly meetings to discuss current goals and maintain a document that tracks completed and active tasks | WIP | Open
Requirements | unclear requirements | It is unclear what each team member needs to complete for an assignment or the overall project | 4 | 4 | 2 | 2*2*2=8 | requirement leader | 2025-05-20 | Use software like Jira to create a list of requirements and delegate tasks to each team member | Created a list of urgent tasks that need to be completed soon in the Discord | Open
| scope creep | It is unclear what each team member is responsible for completing | 2 | 3 | 2 | 4*3*2=24 | requirement leader | 2025-05-16 | Use software like Jira to create a list of requirements and delegate tasks to each team member | WIP | Open
| constant requirements changes | The requirements list is being frequently changed because of too many changes in direction for the project or a lack of understanding of what's required | 2 | 2 | 2 | 4*4*2=32 | requirement leader | 2025-05-20 | Review the requirement list during the team meeting to ensure everything is covered | Not an issue that the team faced | Closed
Management | improper task assignments | Tasks are being assigned to the wrong team members or not at all | 2 | 2 | 1 | 4*4*1=16 | requirement leader | 2025-05-20 | Assign tasks during group meetings in order to capture each group member's input | Not an issue that the team faced | Closed
| improper planning | Portions of the project are planned incorrectly or not at all | 3 | 3 | 3 | 3*3*3=27 | all team members | 2025-05-16 | Use diagrams to visualize the structure of the codebase and easily determine if anything is missing | Not an issue that the team faced | Closed
| lack of management skills | Team members in management roles are having trouble managing the team | 1 | 4 | 5 | 5*2*5=50 | team leader & requirement leader | 2025-05-20 | Possibly switch roles within the team | Not an issue that the team faced | Closed
Technology competence | Not familiar with the framework used | One or more team members haven't used one of the frameworks decided on by the team | 2 | 2 | 2 | 4*4*2=32 | all team members | 2025-05-16 | Research and watch videos to learn about the framework or consider switching frameworks | Not an issue that the team faced | Closed
| Not familiar with the programming language used | One or more team members haven't used the programming language decided on by the team | 2 | 2 | 2 | 4*4*2=32 | all team members | 2025-05-16 | Research and watch videos about the programming language or consider switching to a language everyone is comfortable with | Not an issue that the team faced | Closed
| Not familiar with unit testing | The QA lead hasn't written unit tests before | 2 | 3 | 2 | 4*3*2=24 | qa lead | 2025-05-16 | Research and watch videos about unit testing or switch QA lead role with someone who has more experience | Not an issue that the team faced | Closed
| Other technology incompetence | One or more team members haven't used a technology that they will need to use in order to complete their task | 2 | 2 | 2 | 4*4*2=32 | all team members | 2025-05-20 | Consider using a technology that everyone has some experience with | WIP | Open
| Not familiar with Git | One or more team members haven't used Git/GitHub | 2 | 2 | 1 | 4*4*1=16 | configuration lead | 2025-05-13 | Research how to use Git, complete Lab1, and ask team members for help | Not an issue for anyone | Closed
Design and implementation | Improper design | A software structure that doesn't address the requirements, lacks cohesion between components, violates established principles of good design, etc. | 3 | 5 | 5 | 3*1*5=15 | design lead | 2025-05-20 | Use diagrams to visualize the structure of the codebase and offer explanations for why certain frameworks & technologies are used or necessary | In the process of creating a UML Class diagram | Open
| improper technology stack | The tech stack decided on by the team is inconducive to the vision for the project | 2 | 5 | 5 | 4*1*5=20 | design lead | 2025-05-14 | Justify the use of each component in the tech stack | Used the SPPP doc to justify the use of each component in the tech stack | Closed
| Messy code | The codebase is inconsistently formatted and missing comments | 4 | 4 | 3 | 2*2*4=16 | all team members | 2025-05-20 | Establish programming guidelines and best practices for the group to follow | WIP | Open
Testing | Not enough testing | A lot of the codebase is not automatically tested | 4 | 5 | 3 | 2*1*3=6 | qa lead | 2025-05-27 | Implement unit testing, integration testing, and end-to-end testing | WIP | Open
Integration and deployment | Not enough time for integration and deployment | One or more team members are completing their tasks too close to the deadlines | 4 | 3 | 2 | 2*3*2=12 | all team members | 2025-05-21 | Work earlier in the week so that there is enough time for the group to review everything | WIP | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.